## Checklist - Production(PT7)
Date | 2018-02-06
Environment | PT7(Production)
Upgrade Version From | Tableau 10.3.4
Upgrade Version To | Tableau 10.5.3
Tableau Server Upgrade Checklist
Sl No | Activity | Pre-Upgrade Production | Post-Upgrade Prduction | Result | Comments
1 | Number of Sites are same | 113 | 113 | Succesful
2 | Number of Projects are same (Check for 1 main site AE) | 3 - AE | 3 - AE | Succesful
3 | Number of users | 3430 | 3430 | Succesful
4 | Amount of Data on the servers(Check for 1 main site AE) | 7.08 GB | 7.08 GB | Succesful
5 | Check the mobile connectivity to the server | Not tested | Not tested | Succesful
6 | Rest-API runs fine | Running fine | Running fine | Succesful
7 | Backup runs fine | Running fine | Running fine | Succesful
8 | Check all the necessary drivers installed on the server | Checked | Checked | Succesful
9 | Email subscription verification | Checked | Checked | Succesful
10 | Extracts running correctly | Running fine | Running fine | Succesful
11 | Tableau server desktop license management feature | Checked | Checked | Succesful
12 | Check for Project settings and permissions(Check for 1 main site) | Locked to project with 24 groups assigned to AA_IconA | Locked to project with 24 groups assigned to AA_IconA | Succesful
13 | Publishing to the Server from Tableau Desktop | Checked | Checked | Succesful
14 | Web edit of the Server(check in Tableau Admin site) | Checked | Checked | Succesful
15 | Verify Published Dashboards (Check for 1 main site) | Checked | Checked | Succesful
16 | Check if the necessary drivers are installed | Checked | Checked | Succesful
| Backup file | D:\Program Files\Tableau\Maintenance\Backups\TableauServer_Backup-2018-06-02-PreUpgrade.tsbak